Miri Landmark Property Enterprise

# Budget Plan

Prototype-first plan  |  ≈ 100 units, 3 staff  |  Prices checked October 2026  |  v3.1

# 1. Summary

Phase 1 (rent tracker, one-click WhatsApp reminders and Sarawak Energy) needs no office hardware and no messaging or AI costs: reminders use free WhatsApp click-to-chat links on the company number. Costs rise in later phases as automatic WhatsApp sending, AI receipt reading and the office-based water bot are added.

| Stage | One-time | Monthly | Per year |
| --- | --- | --- | --- |
| Phase 1 prototype (cloud, recommended) | ≈ RM60 (domain) | ≈ RM55 | ≈ RM720 |
| Phase 1 go-live with daily backups | ≈ RM60 (domain) | ≈ RM160 | ≈ RM1,980 |
| Full system, Phases 1–4 | RM1,100 – 2,000 | ≈ RM250 – 300 | ≈ RM3,000 – 3,600 |

RECOMMENDATION: Run the prototype on a small cloud server with Supabase's free plan (≈ RM55/month). Upgrade the database to Supabase Pro (≈ +RM105/month) at go-live so the records have automatic daily backups.

# 2. Assumptions

- About 100 units and 3 staff; prices converted at RM4.20 per USD (mid-market ≈ RM4.09, plus card FX fees).

- List prices as of October 2026; they can change. Foreign digital services may attract 8% service tax where charged.

- Development work is shown separately (Section 6). Hardware prices are retail estimates; get local quotes.

# 3. Phase 1 Hosting Options

All three give the same features. Phase 1 has no tenant-facing parts, so short outages only affect staff, which makes the cheaper options reasonable.

| Option | What runs where | Monthly | Trade-off |
| --- | --- | --- | --- |
| A. Office PC | Portal, worker on an office mini PC; Supabase free; Cloudflare Tunnel | ≈ RM10 (+ RM1,050–1,750 hardware) | Cheapest to run; stops during office power or internet cuts; hardware to maintain |
| B. Lean cloud (prototype) | Portal + worker on a 2GB VPS (US$12); Supabase free | ≈ RM55 | No hardware; no automatic database backups (weekly manual dump) |
| C. Standard cloud (go-live) | As B, with Supabase Pro (US$25) | ≈ RM160 | Daily automatic backups, no project pausing; the recommended long-term setup |

## 3.1 Monthly breakdown (Options B and C)

| Item | USD | RM / month |
| --- | --- | --- |
| VPS, Singapore, 2GB RAM (portal + worker + scraper) | 12 | ≈ 50 |
| Supabase Free (prototype) / Pro (go-live) | 0 / 25 | 0 / ≈ 105 |
| Domain (yearly cost spread monthly) | – | ≈ 5 |
| Cloudflare Tunnel + Access (up to 50 users) | Free | 0 |
| WhatsApp reminders (click-to-chat, company number) | Free | 0 |
| Total: Option B / Option C |  | ≈ RM55 / RM160 |

Supabase's free plan includes a 500MB database and a small file-storage allowance: plenty for ~100 units' records, and enough receipt photos for the prototype if images are kept reasonably small.

# 4. Later Phases: What Gets Added

| Phase | New costs (≈ 100 units) | One-time |
| --- | --- | --- |
| 2. WhatsApp automation | WhatsApp utility messages ≈ RM65 + replies above 1,000 free ≈ RM10; AI receipt reading ≈ RM10; possibly a 4GB VPS for n8n (+≈ RM50) | Prepaid SIM for a dedicated number (RM10–30), if not keeping the existing number |
| 3. Landlords & accounting | None (uses existing server and database) | An office PC that stays on for SQL Account extraction (or reuse the accounting PC) |
| 4. Water & maintenance | Electricity for the office PC ≈ RM5 | Dedicated Android phone RM300–600; mini PC RM800–1,300 if no suitable office PC; UPS RM250–450 |

WhatsApp rates (Malaysia): utility templates ≈ RM0.0564 each; replies to tenant messages free for the first 1,000 per month, then ≈ RM0.0564 each. Sending staff alerts to one main PIC instead of three saves about RM20/month in Phase 2.

# 5. Optional Add-Ons

| Add-on | Estimate | When |
| --- | --- | --- |
| Google Workspace Business Starter (company-owned files) | ≈ RM28 / user / month | Before Phase 2, so tenant documents belong to the company |
| Larger VPS (4GB) | +≈ RM50 / month | If the portal slows down, or when n8n is added |
| Supabase Pro earlier (during prototype) | +≈ RM105 / month | If the office wants automatic backups from day one |
| Outsourced portal UI work | Get quotes | To shorten the timeline |

# 6. Effort

## 6.1 Phase 1 development (Nash, part-time)

| Work package | Estimate |
| --- | --- |
| Database, register template and importer | 1 – 2 weeks |
| Rent schedule, payments, staff portal pages | 2 – 3 weeks |
| Today page, WhatsApp reminder queue, follow-ups, reports | 1 – 1.5 weeks |
| Bank statement matching | 1 – 1.5 weeks |
| Sarawak Energy scraper | 1 – 2 weeks |
| Deployment, testing, staff training | 1 week |
| Total | ≈ 6 – 8 weeks |

## 6.2 Staff time to rebuild the records

Rebuilding the register is the biggest hidden cost of Phase 1: about 10–15 minutes per unit, or roughly 17–25 staff-hours in total (≈ 6–8 hours per staff member for their own portfolio). The one-month parallel run adds a few minutes per payment while both the sheet and the portal are updated.

# 7. Recommended Path

| When | What | Monthly | Decide |
| --- | --- | --- | --- |
| Weeks 1–6 | Build and test on a laptop, then deploy to the VPS (Option B) | ≈ RM0 – 55 | — |
| Weeks 6–8 | Parallel run with the sheet | ≈ RM55 | Switch over? |
| Go-live | Upgrade to Supabase Pro (Option C) | ≈ RM160 | Start Phase 2? |
| Phase 2+ | Add WhatsApp, AI, then office hardware for Phases 3–4 | ≈ RM250 – 300 | Per phase |

# 8. Cost Controls

- Supabase Pro has a spend cap on by default; keep it on.

- Phase 1 messaging is free (click-to-chat); paid WhatsApp API messages start only when Phase 2 is approved.

- Review the VPS and Supabase invoices monthly for the first three months.

- Buy Phase 4 hardware only after the water feasibility check confirms the bot approach.

# 9. Decisions

- Approve Phase 1 on Option B (≈ RM55/month) plus a domain (≈ RM60/year).

- Agree staff time for rebuilding the register (≈ 6–8 hours each).

- Agree to upgrade to Supabase Pro (≈ RM160/month total) at go-live.

- Decide on Phase 2 after the parallel run.

Price sources (October 2026): DigitalOcean, Supabase, Cloudflare, Meta WhatsApp Malaysia rate card, Anthropic and Google Workspace Malaysia pricing pages and published summaries.